## PP- NYSE Updates (2)
New CT Plan Tracker
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN MONTH START | PLAN DURATION (IN MONTHS) | ACTUAL MONTH START | ACTUAL DURATION (IN MONTHS) | PERCENT COMPLETE | PERIODS (in months)
[7 empty] | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
Workstream 1: Set Up CT Plan Governance (Dependent on SEC approval of CT Plan)
1.1 | Designation of Member Representatives | 1 | 1 | 1 | 1 | 100% | [37 empty] | 2
1.2 | Determine interim funding (to pay for counsel, RFP advisory firm, Administrator, etc.) | 1 | 2 | 1 | 2 | 0% | [37 empty] | 3
1.3 | Hire Outside Counsel | 2 | 0.25 | 2 | 0.25 | 100% | [37 empty] | 2.25
1.4 | Hire Communications Firm | 2 | 0.25 | 2 | 0.25 | 0% | [37 empty] | 2.25
1.5 | Advisory Committee Formation - announcement - interviews - OpCo Vote | 2 | 3 | 2 | 3 | 0% | 2025-02-01: 2025-02-19 | 5
1.6 | Engage Processor(s) - Contracts - SLAs | 4 | 6 |  |  | 0% | [37 empty] | 0
Workstream 2: New Fees, Policies, and Data Subscriber Agreements (Dependent on Advisory Committee formation - To be prepared in parallel with Workflow process to select new Administrator)
2.1 | OpCo and Advisory Committees to determine new fees/policies | 4 | 7 |  |  | 0% | [37 empty] | 0
2.2 | Draft fee filing (and any related policies that need to be filed) | 11 | 1 |  |  | 0% | [37 empty] | 0
2.3 | File and Obtain approval of fee filing | 12 | 10 |  |  | 0% | [37 empty] | 0
2.4 | OpCo and Advisory Committees to determine policies (to the extent separate from fee filing, e.g., direct v indirect bill) | 4 | 9 |  |  | 0% | 2025-11-01: 2025-11-19 | 0
2.5 | OpCo to work with counsel to develop new data subscriber agreements | 13 | 5 |  |  | 0% | [37 empty] | 0
Workstream 3: Selection of New Administrator (Dependent on Advisory Committee Formation and Interim Funding)
3.1 | Hire Advisory Firm To Manage RFI/RFP Process - announcement - interviews - decision | 4 | 1 |  |  | 0% | [37 empty] | 0
3.2 | Draft RFP for New Administrator | 5 | 2 |  |  | 0% | [37 empty] | #REF!
3.3 | Advertise & Solicite Response to RFP | 7 | 2 |  |  | 0% | [37 empty] | 0
3.4 | Advisory firm evaluates bids and provides preliminary recommendations (e.g., narrowing of bids) | 9 | 1 |  |  | 0% | [37 empty] | #REF!
3.5 | Operating Committee conducts Interviews ( potential for revised bids, subject to quality of RFP responses) | 10 | 4 |  |  | 0% | [37 empty] | #REF!
3.6 | Operating Committee votes on New Administrator | 14 | 1 |  |  | 0% | [37 empty] | 0
| Workstream 4: Contract Negotiations with New Administrator (Potentially dependent on fees and policies being finalized, which could impact scope of services) | [42 empty] | #REF!
4.1 | Operating Committee negotiates Administrative Services Agreement and SLAs with New Administrator | 15 | 4 |  |  | 0% | [37 empty] | #REF!
| Workstream 5: Administrator Setup (Dependent on fees, policies, and data subscriber agreements being finalized and contract/SLA with new Administrator executed) | [42 empty] | 0
5.1 | Develop systems that tailor to Plan requirements to support account information, track vendor relationships, billing, interactive licensing tool. Allow for customers to: • View account profile, subscriptions, entities they are redistributing • View invoices • Report usage and external redistribution • Submit contracts online • Submit data feed requests *Dependent on Firm Setup* | 19 | 3 |  |  | 0% | [37 empty] | 0
5.2 | Hire Staff to support all functions (e.g., customer services/account management, customer audits, Plan services, accounting) | 19 | 3 |  |  | 0% | [37 empty] | 0
5.3 | Transfer existing customer data from UTP and CTA plans to new Administrator | 20 | 5 |  |  | 0%
5.4 | Standup New Plan Website | 19 | 3 |  |  | 0% | [37 empty] | 0
5.5 | Customer announcements (communicating transition timing and deadlines) | 22 | 8 |  |  | 0%
5.6 | Contractually repaper all customers to new data subscriber agreements | 23 | 4 |  |  | 0% | [37 empty] | 0
5.7 | Customer onboarding to new systems | 25 | 5 |  |  | 0% | [37 empty] | 0
5.8 | Set up financial workflow for the Plan - financial statements to the Plan - coordinate with Processors on revenue allocation - manage Plan expenses and payments - support Plan audit requirements including SOX, tax, annual, statutory | 21 | 4 |  |  | 0% | [37 empty] | 0
5.9 | Set up support for Plan governance (e.g., online board books, voting portal, document repository, drafting and tracking compliance with Confidentiality Policy and Conflicts Policy) | 21 | 6 |  |  | 0% | [37 empty] | 0
| Workstream 6: Retirement of current plans - orderly transition (Dependent on fees being approved, policies finalized, and Administrator fully ready to support all functions) | [42 empty] | 0
6.1 | CTA/UTP Plans file to cease operations (dependent on SEC approval of CT Plan fee filing) | 23 | 2 |  |  | 0% | [37 empty] | 0
6.2 | New Administrator begins Operations | 30 | 1 |  |  | 0% | [37 empty] | 0
6.3 | Assess whether current administrators need to continue after end of CTA/UTP operations to finish bill collection etc, or if those services transfer to new administrator | 23 | 1 |  |  | 0% | [37 empty] | 0
0
0
0
0

## CT Plan Workflows_NYSE
Workflow | Description | Subtasks
1 | Set up CT Plan Governance (Dependent on CT Plan approval)
|  | 1.1 | Designation of Member representatives
|  | 1.2 | Determine interim funding (to pay for counsel, RFP advisory firm, Administrator, etc.)
|  | 1.3 | Hire outside counsel
|  | 1.4 | Hire communications firm
|  | 1.5 | Advisory Committee formation: - Announcement - Interviews - OpCo vote
|  | 1.6 | Engage Processor(s) - contracts - SLAs
2 | New fees, policies, and data subscriber agreements (Dependent on Advisory Committee formation - To be prepared in parallel with Workflow process to select new Administrator)
|  | 2.1 | OpCo and Advisory Committees to determine new fees/policies
|  | 2.2 | Draft fee filing (and any related policies that need to be filed)
|  | 2.3 | File and obtain approval of fee filing
|  | 2.4 | OpCo and Advisory Committees to determine policies (to the extent separate from fee filing, e.g., direct v indirect bill)
|  | 2.5 | OpCo to work with counsel to develop new data subscriber agreements
3 | Selection of New Administrator (Dependent on Advisory Committee formation and interim funding)
|  | 3.1 | Hire advisory firm To manage RFI/RFP Process: - announcement - interviews - decision - contract
|  | 3.2 | Draft RFI
|  | 3.3 | Advertise and solicit response to RFI
|  | 3.4 | Response period for RFI
|  | 3.5 | Review responses to RFI
|  | 3.6 | Draft RFP for new administrator
|  | 3.7 | Advertise and solicit response to RFP
|  | 3.8 | Response period for RFP
|  | 3.9 | Review Responses to RFP
|  | 3.1 | Advisory firm evaluates bids and provides preliminary recommendations (e.g., narrowing of bids)
|  | 3.11 | Operating Committee conducts interviews (potential for revised bids - subject to quality of RFP responses)
|  | 3.12 | Operating Committee votes on new Administrator
4 | Contract negotiations with new Administrator (Potentially dependent on fees and policies being finalized, which could impact scope of services)
|  | 4.1 | Operating Committee negotiates Administrative Services Agreement with new Administrator
|  | 4.2 | Negotiate SLAs (e.g., performance standards regarding legal, audit, tax, IT, etc.)
5 | Administrator set up (Dependent on fees, policies, and data subscriber agreements being finalized)
|  | 5.1 | Develop systems that tailor to Plan requirements to support account information, track vendor relationships, billing, interactive licensing tool. Allow for customers to: • View account profile, subscriptions, entities they are redistributing • View invoices • Report usage and external redistribution • Submit contracts online • Submit data feed requests
|  | 5.2 | Hire staff to support all functions (e.g., customer services/account management, customer audits, Plan services, accounting)
|  | 5.3 | Transfer existing customer data from UTP and CTA plans to new Administrator
|  | 5.4 | Setup new Plan website
|  | 5.5 | Customer announcements (communicating transition timing and deadlines)
|  | 5.6 | Contractually repaper all customers to new data subscriber agreements
|  | 5.7 | Customer onboarding to new systems
|  | 5.8 | Draft customer audit procedures
|  | 5.9 | Set up financial workflow for the Plan - financial statements to the Plan - coordinate with Processors on revenue allocation - manage Plan expenses and payments - support Plan audit requirements including SOX, tax, annual, statutory
|  | 5.1 | Set up support for Plan governance (e.g., online board books, voting portal, document repository, tracking compliance with Confidentiality Policy and Conflicts Policy)
6 | Retirement of current plans - orderly transition (Dependent on fees being approved, policies finalized, and Administrator fully ready to support all functions)
|  | 6.1 | CTA/UTP Plans file to cease operations
|  | 6.2 | New Administrator begins operations
|  | 6.3 | Assess whether current administrators need to continue after end of CTA/UTP operations to finish bill collection etc, or if those services transfer to new administrator